## Best
taskID | task | predecessorTaskIDs | bestCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product |  | 3 | 3 | 0 | 0 | 0 | 0
B | Develop marketing strategy |  | 3 | 3 | 0 | 0 | 0 | 0
C | Design brochure | A | 24 | 4 | 8 | 8 | 0 | 4
D | Develop product prototype |  | 50 | 5 | 15 | 15 | 0 | 15
D1 | Requirements analysis | A | 24 | 2 | 8 | 0 | 4 | 10
D2 | Software design | D1 | 24 | 2 | 10 | 2 | 0 | 10
D3 | System design | D1 | 24 | 2 | 10 | 5 | 0 | 7
D4 | Coding | D2, D3 | 50 | 3 | 20 | 15 | 0 | 12
D5 | Write documentation | D4 | 50 | 5 | 15 | 15 | 0 | 15
D6 | Unit testing | D4 | 50 | 4 | 0 | 20 | 6 | 20
D7 | System testing | D6 | 50 | 5 | 0 | 20 | 10 | 15
D8 | Package deliverables | D5, D7 | 50 | 5 | 0 | 20 | 0 | 25
E | Survey potential market | B, C | 24 | 6 | 0 | 0 | 18 | 0
F | Develop pricing plan | D8, E | 24 | 6 | 0 | 0 | 18 | 0
G | Develop implementation plan | A, D8 | 24 | 8 | 0 | 0 | 16 | 0
H | Write client proposal | F, G | 8 | 3 | 0 | 0 | 5 | 0

## expected
taskID | task | predecessorTaskIDs | expectedHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product |  | 6 | 6 | 0 | 0 | 0 | 0
B | Develop marketing strategy |  | 6 | 6 | 0 | 0 | 0 | 0
C | Design brochure | A | 40 | 6.7 | 13.3 | 13.3 | 0 | 6.7
D | Develop product prototype |  | 80 | 8 | 24 | 24 | 0 | 24
D1 | Requirements analysis | A | 40 | 3.3 | 13.3 | 0 | 6.7 | 16.7
D2 | Software design | D1 | 40 | 3.3 | 16.7 | 3.3 | 0 | 16.7
D3 | System design | D1 | 40 | 3.3 | 16.7 | 8.3 | 0 | 11.7
D4 | Coding | D2, D3 | 80 | 4.8 | 32 | 24 | 0 | 19.2
D5 | Write documentation | D4 | 80 | 8 | 24 | 24 | 0 | 24
D6 | Unit testing | D4 | 80 | 6.4 | 0 | 32 | 9.6 | 32
D7 | System testing | D6 | 80 | 8 | 0 | 32 | 16 | 24
D8 | Package deliverables | D5, D7 | 80 | 8 | 0 | 32 | 0 | 40
E | Survey potential market | B, C | 40 | 10 | 0 | 0 | 30 | 0
F | Develop pricing plan | D8, E | 40 | 10 | 0 | 0 | 30 | 0
G | Develop implementation plan | A, D8 | 40 | 13.3 | 0 | 0 | 26.7 | 0
H | Write client proposal | F, G | 15 | 5.6 | 0 | 0 | 9.4 | 0

## worst
taskID | task | predecessorTaskIDs | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product |  | 9 | 9 | 0 | 0 | 0 | 0
B | Develop marketing strategy |  | 9 | 9 | 0 | 0 | 0 | 0
C | Design brochure | A | 60 | 10 | 20 | 20 | 0 | 10
D | Develop product prototype |  | 120 | 12 | 36 | 36 | 0 | 36
D1 | Requirements analysis | A | 60 | 5 | 20 | 0 | 10 | 25
D2 | Software design | D1 | 60 | 5 | 25 | 5 | 0 | 25
D3 | System design | D1 | 60 | 5 | 25 | 12.5 | 0 | 17.5
D4 | Coding | D2, D3 | 120 | 7.2 | 48 | 36 | 0 | 28.8
D5 | Write documentation | D4 | 120 | 12 | 36 | 36 | 0 | 36
D6 | Unit testing | D4 | 120 | 9.6 | 0 | 48 | 14.4 | 48
D7 | System testing | D6 | 120 | 12 | 0 | 48 | 24 | 36
D8 | Package deliverables | D5, D7 | 120 | 12 | 0 | 48 | 0 | 60
E | Survey potential market | B, C | 60 | 15 | 0 | 0 | 45 | 0
F | Develop pricing plan | D8, E | 60 | 15 | 0 | 0 | 45 | 0
G | Develop implementation plan | A, D8 | 60 | 20 | 0 | 0 | 40 | 0
H | Write client proposal | F, G | 24 | 9 | 0 | 0 | 15 | 0

## Cost
projectManager | $50/ hour
frontendDeveloper | $45/ hour
backendDeveloper | $45/ hour
dataScientist | $60/hour
dataEngineer | $55/ hour